## AgencyPortfolio
Portfolio | Non-Corporate Commonwealth Entity | AgencyShortName
Portfolio_I | Agency A | AGA
Portfolio_I | Agency A | AGA
Portfolio_I | Agency A | AGA
Portfolio_I | Agency A | AGA
Portfolio_I | Agency A | AGA
Portfolio_I | Agency B | AGB
Portfolio_I | Agency B | AGB
Portfolio_I | Agency B | AGB
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC
Portfolio_II | Agency C | AGC

## PP_Assessments
AgencyShortName | ProjectID | CollectionRound | Project Program Name | ProjectProgram_Start_Date | ProjectProgram_Completion_Date | Budget_Funded | Total_Budget | Total_Spend_To_Date | ICT_Budget | Time_Score | Time_Score_Note | ICT_Cost_Score | Spend_Time_Deviation | Spend_Percentage | Time_Percentage | Overall_Benefit_Viability_Assessor | Overall_Benefit_Status_Assessor | Overall_Benefit_Rating | Overall_Benefit_Assessor_Note | Overall_Risk_LogicalCompleteCurrent | Overall_Risk_ResidualRisks | Overall_Risk_Assessor | Overall_Risk_Assessor_Note | DeliveryConfidence_Assessor_Note | Public_Impact_Population | Public_Impact_Quantum | Public_Impact_Score | Public_Impact_Score_Note | General_Note | Recommendations | Duration | Assessment Priority | DeliveryConfidence_Assessor_Score | ProjectProgram_Type | ProjectProgram_Objectives | Overall_Risk_ResidualRisks_Score | Delivery Confidence DIMO | Age_Year | Year | WeekOfYear | Delivery Confidence Agency | Total_Budget_Format | StatusCommentary_Agency | Agency_Coordinator_Email | Agency_SRO_Email | Assessment Priority (groups) | Delivery Confidence DIMO (groups) | ICT_Cost_Score (groups) | Delivery_Confidence_Updated | Delivery Confidence Agency (groups)
AGA | AGA_001 | Q2_2017 | Project Program 1 | 2015-07-01 | 2017-12-30 | Yes | 14744906 | 86028000 | 183620000 | 70-90% | None | <$20m | <>25-50% | 81.33% | 59.41% | 2 | 1 | 3 | Assessor generated text | Most risks and mitigations are NOT logical, complete or current | All of the residual risks are low or medium | 3 | Assessor generated text | A green-amber rating has been assigned as the benefits identified do not appear to have been realised after 8 years of work and operations - risks appear to have been adequately identified with mitigation and controls applied. | 2 - Population - Medium | 1 - Quantum - Low | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 3352 | Involve | 2 | Project | Agency generated text | 1 | Green-Amber | 2018.4808 | 2017 | 26 | Green-Amber | $25.9M | Agency generated text | firstname.lastname@Agency-A.gov.au | firstname.lastname@AGA_001.gov.au | 2_Involve | 4_Green_Amber | 1. <$20m | Updated | 4_Green_Amber
AGA | AGA_002 | Q2_2017 | Project Program 2 | 2011-01-11 | 2017-06-30 | Yes | 32785011 | 118060000 | 11915000 | 70-90% | None | <$20m | <>25-50% | 12.71% | 26.05% | 3 | 4 | 1 | Assessor generated text | All risks and mitigations are logical, complete and current | Any of the residual risks are High | 3 | Assessor generated text |  | 3 - Population - High | 1 - Quantum - Low | 1 | Assessor generated text | Assessor generated text | Assessor generated text | 2176 | Involve | 4 | Project | Agency generated text | 2 | Amber-Red | 2017.5 | 2020 | 27 |  | $175.3M | Agency generated text | firstname.lastname@Agency-A.gov.au | firstname.lastname@AGA_002.gov.au | 2_Involve | 4_Amber-Red | 3. $100m-$300m | Updated | 4_Amber-Red
AGA | AGA_003 | Q2_2017 | Project Program 3 | 2017-01-01 | 2017-06-30 | Yes | 175300000 | 95877000 | 212475000 | 20-50% | None | $20m-$100m | <>25-50% | 10.08% | 89.67% | 2 | 4 | 3 | Assessor generated text | All risks and mitigations are logical, complete and current | Any of the residual risks are High | 3 | Assessor generated text |  | 1 - Population - Low | 3 - Quantum - High | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 1826 | Involve | 3 | Program | Agency generated text | 2 | Amber-Red | 2018.2308 | 2020 | 38 | Green-Amber | $516.5M | Agency generated text | firstname.lastname@Agency-A.gov.au | firstname.lastname@AGA_003.gov.au | 2_Involve | 4_Amber-Red | 2. $20m-$100m | Not updated | 4_Amber-Red
AGA | AGA_004 | Q2_2017 | Project Program 4 | 2016-07-01 | 2018-06-30 | Yes | 16870000 | 118060000 | 31138054 | 20-50% | None | <$20m | <>15% | 94.79% | 35.65% | 2 | 3 | 3 | Assessor generated text | Most risks and mitigations are NOT logical, complete or current | Any of the residual risks are Extreme OR no risks have been provided | 5 | Assessor generated text | No risks identified or provide. Benefits are not identified as beings incrementally realised. | 3 - Population - High | 2 - Quantum - Medium | 3 | Assessor generated text | Assessor generated text | Assessor generated text | 741 | Engage | 4 | Project | Agency generated text | 3 | Amber-Red | 2017.8654 | 2017 | 38 | Red | $56.9M | Agency generated text | firstname.lastname@Agency-A.gov.au | firstname.lastname@AGA_004.gov.au | 3_Engage | 4_Amber-Red | 3. $100m-$300m | Updated | 4_Amber-Red
AGA | AGA_005 | Q2_2017 | Project Program 5 | 2015-04-01 | 2020-03-31 | Yes | 31138054 | 0 | 43690000 | >90% | None | $20m-$100m | <>15% | 55.34% | 75.67% | 2 | 3 | 4 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text | the project has already experienced a delay and has some potential to face more unplanned scheduling and resourcing risks | 1 - Population - Low | 1 - Quantum - Low | 5 | Assessor generated text | Assessor generated text | Assessor generated text | 1457 | Involve | 5 | Project | Agency generated text | 1 | Green-Amber | 2020.25 | 2017 | 26 | Green | $220.40M | Agency generated text | firstname.lastname@Agency-A.gov.au | firstname.lastname@AGA_005.gov.au | 2_Involve | 4_Green_Amber | 1. <$20m | Updated | 4_Green_Amber
AGB | AGB_001 | Q2_2017 | Project Program 6 | 2016-07-01 | 2017-12-31 | Yes | 101148000 | 171088000 | 101148000 | 20-50% | None | <$20m | <>15% | 94.79% | 78.3% | 2 | 3 | 3 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text |  | 2 - Population - Medium | 3 - Quantum - High | 5 | Assessor generated text | Assessor generated text | Assessor generated text | 1460 | Involve | 3 | Program | Agency generated text | 1 | Amber-Red | 2018 | 2017 | 27 | Amber | $23.2M | Agency generated text | firstname.lastname@Agency-B.gov.au | firstname.lastname@AGB_001.gov.au | 2_Involve | 4_Amber-Red | 1. <$20m | Updated | 4_Amber-Red
AGB | AGB_002 | Q2_2017 | Project Program 7 | 2015-05-25 | 2018-06-30 | Yes | 16870000 | 6970000 | 43690000 | 20-50% | None | $20m-$100m | <>15% | 20.03% | 75.67% | 1 | 3 | 1 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text | there is likely to be a strong impetus culturally for this project to succeed given the nature of the issues it is seeking to mitigate - ie death and injuries to AFP personnel in terrorist-related acts in recent years. | 3 - Population - High | 1 - Quantum - Low | 4 | Assessor generated text | Assessor generated text | Assessor generated text | 730 | Engage | 4 | Project | Agency generated text | 1 | Amber | 2020.25 | 2018 | 27 | Green-Amber | $457.4M | Agency generated text | firstname.lastname@Agency-B.gov.au | firstname.lastname@AGB_002.gov.au | 3_Engage | 3_Amber | 1. <$20m | Not updated | 3_Amber
AGB | AGB_003 | Q2_2017 | Project Program 8 | 2016-07-01 | 2018-06-30 | Yes | 457370000 | 11910000 | 0 | 70-90% | None | <$20m | <>15-25% | 0% | 35.65% | 1 | 3 | 4 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text |  | 3 - Population - High | 2 - Quantum - Medium | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 1094 | Involve | 4 | Project | Agency generated text | 1 | Amber | 2020.5 | 2017 | 26 | Amber | $95.4M | Agency generated text | firstname.lastname@Agency-B.gov.au | firstname.lastname@AGB_003.gov.au | 2_Involve | 3_Amber | 2. $20m-$100m | Updated | 3_Amber
AGC | AGC_001 | Q2_2017 | Project Program 9 | 2015-07-01 | 2019-03-09 | Yes | 24680000 | 10100000 | 21740000 | 70-90% | None | $20m-$100m | <>25-50% | 94.79% | 77.39% | 1 | 1 | 4 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text | the project may be successfully delivered after December 2019 however no benefits will be realised before then. This creates a collective project risk in the event of a major incident occurring affecting the AFP's ability to deliver community policing, protection, surveillance and tactical operations before project completion. | 1 - Population - Low | 3 - Quantum - High | 4 | Assessor generated text | Assessor generated text | Assessor generated text | 1278 | Involve | 1 | Project | Agency generated text | 1 | Red | 2020.5 | 2020 | 27 | Green-Amber | $32.8M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_001.gov.au | 2_Involve | 5_Red | 1. <$20m | Not updated | 5_Red
AGC | AGC_002 | Q2_2017 | Project Program 10 | 2016-10-25 | 2019-03-09 | Yes | 46302000 | 133733000 | 31138054 | 20-50% | None | $20m-$100m | <>15% | 94.79% | 35.65% | 3 | 4 | 5 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text |  | 2 - Population - Medium | 2 - Quantum - Medium | 4 | Assessor generated text | Assessor generated text | Assessor generated text | 1034 | Engage | 4 | Project | Agency generated text | 1 | Amber-Red | 2020.5 | 2018 | 53 | Amber | $516.5M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_002.gov.au | 3_Engage | 4_Amber-Red | 2. $20m-$100m | Updated | 4_Amber-Red
AGC | AGC_003 | Q2_2017 | Project Program 11 | 2013-07-01 | 2017-11-06 | Yes | 11140000 | 17960000 | 0 | 20-50% | None | <$20m | <>25-50% | 54.59% | 90.71% | 2 | 4 | 3 | Assessor generated text | All risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 1 | Assessor generated text |  | 3 - Population - High | 2 - Quantum - Medium | 3 | Assessor generated text | Assessor generated text | Assessor generated text | 1702 | Involve | 1 | Project | Agency generated text | 1 | Amber-Red | 2018.2308 | 2018 | 52 | Green-Amber | $516.5M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_003.gov.au | 2_Involve | 4_Amber-Red | 2. $20m-$100m | Updated | 4_Amber-Red
AGC | AGC_004 | Q2_2017 | Project Program 12 | 2015-07-01 | 2020-06-30 | Yes | 175300000 | 122000000 | 13550711 | 20-50% | None | $20m-$100m | <>15-25% | 77.11% | 76.79% | 3 | 4 | 3 | Assessor generated text | Some risks and mitigations are logical, complete and current | Any of the residual risks are High | 3 | Assessor generated text | There are a couple of risks and benefits that should be discussed, It would be good to know the timeing of the exception report and when recommended changes would be made. | 3 - Population - High | 2 - Quantum - Medium | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 1399 | Engage | 5 | Project | Agency generated text | 2 | Amber | 2017.5 | 2020 | 27 | Amber | $222.4M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_004.gov.au | 3_Engage | 3_Amber | 2. $20m-$100m | Not updated | 3_Amber
AGC | AGC_005 | Q2_2017 | Project Program 13 | 2010-04-01 | 2018-06-30 | Yes | 220450000 | 9420000 | 43690000 | 70-90% | None | <$20m | <>25-50% | 36.63% | 77.39% | 2 | 4 | 4 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text | Should be more information provided on non-IT technical risks not just IT technical risks, however they are significant as the lack of stability in the ATO's IT environment has impacted all IT projects. Would like to see the risks associated with delivery of the "what does success look like" points, to ensure that they are tracked and managed This project should be discussed with the ATO to check the questions outlined above. | 3 - Population - High | 3 - Quantum - High | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 2098 | Involve | 2 | Program | Agency generated text | 1 | Green | 2017.7115 | 2017 | 27 | Green | $23.2M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_005.gov.au | 2_Involve | 5_Green | 2. $20m-$100m | Updated | 5_Green
AGC | AGC_006 | Q2_2017 | Project Program 14 | 2013-07-01 | 2020-07-28 | Yes | 89650000 | 9420000 | 24310497 | 50-70% | None | <$20m | <>25-50% | 0% | 77.65% | 3 | 3 | 2 | Assessor generated text | All risks and mitigations are logical, complete and current | Any of the residual risks are High | 3 | Assessor generated text | While DIMO will need to discuss this project further with the ATO, hopefully there can be better explenation of the questions that we currently have. This project probably should be thought about as something that has ongoing engagment with DIMO | 3 - Population - High | 2 - Quantum - Medium | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 1654 | Involve | 3 | Project | Agency generated text | 2 | Amber | 2018.6538 | 2020 | 38 | Green-Amber | $25.9M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_006.gov.au | 2_Involve | 3_Amber | 1. <$20m | Updated | 3_Amber
AGC | AGC_007 | Q2_2017 | Project Program 15 | 2015-07-01 | 2018-12-30 | Yes | 31138054 | 14862000 | 21740000 | 20-50% | None | <$20m | <>15% | 0% | 59.41% | 1 | 3 | 2 | Assessor generated text | All risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 1 | Assessor generated text | This program is mature and clearly has a good handle on governance. The Gateway review was rated Green. | 3 - Population - High | 1 - Quantum - Low | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 2740 | Involve | 3 | Project | Agency generated text | 1 | Amber | 2020.5 | 2018 | 26 | Amber | $25.9M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_007.gov.au | 2_Involve | 3_Amber | 1. <$20m | Not updated | 3_Amber
AGC | AGC_008 | Q2_2017 | NULL EVERYTHING
AGC | AGC_009 | Q2_2017 | NULL BUDGETS | 2015-05-25 | 2017-09-11 | Yes |  | 5887000 |  | 50-70% | None | <$20m | <>15-25% | 57.42% | 35.65% | 2 | 3 | 5 | Assessor generated text | All risks and mitigations are logical, complete and current | Any of the residual risks are High | 3 | Assessor generated text | the adoption of an agile methodology appears to be generating some positive outcomes for the project thus far. | 3 - Population - High | 2 - Quantum - Medium | 4 | Assessor generated text | Assessor generated text | Assessor generated text | 1520 | Engage | 3 | Program | Agency generated text | 2 | Green-Amber | 2018.6538 | 2019 | 31 | Green | $284.7M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_009.gov.au | 3_Engage | 4_Green_Amber | 2. $20m-$100m | Updated | 4_Green_Amber
AGC | AGC_010 | Q2_2017 | NULL SPENT | 2015-11-01 | 2018-09-01 | Yes | 11915000 | 14800000 | 21740000 | 50-70% | None | $20m-$100m | <>15% |  | 81.98% | 2 | 3 | 3 | Assessor generated text | Some risks and mitigations are logical, complete and current | All of the residual risks are low or medium | 2 | Assessor generated text | Project appears to have realistic assessment of risks and benefits, and had transparently reported one of the benefits "at risk". Linkages between benefits status and risk mitigations are compelling. Internal resourcing appears to be a consistent risk them amongst Bureau projects | 3 - Population - High | 2 - Quantum - Medium | 2 | Assessor generated text | Assessor generated text | Assessor generated text | 1827 | Engage | 5 | Project | Agency generated text | 1 | Amber | 2019.1731 | 2020 | 27 | Green | $21.6M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_010.gov.au | 3_Engage | 3_Amber | 2. $20m-$100m | Updated | 3_Amber
AGC | AGC_011 | Q2_2017 | NULL PROGRESS | 2017-01-01 | 2020-06-30 | Yes | 150000000 | 0 | 43690000 | <20% | None | <$20m | <>15% | 63.73% |  | 3 | 4 | 2 | Assessor generated text | Most risks and mitigations are NOT logical, complete or current | All of the residual risks are low or medium | 3 | Assessor generated text | This project appears to be underspent, has unclear objectives and has much logical overlap with ROBUST. Benefits and risks are vague, with unclear measurement criteria or impact statements and don't appear to have been updated since project inception. | 1 - Population - Low | 1 - Quantum - Low | 4 | Assessor generated text | Assessor generated text | Assessor generated text | 2001 | Involve | 1 | Project | Agency generated text | 1 | Amber | 2020.5769 | 2017 | 53 | Amber | $11.9M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_011.gov.au | 2_Involve | 3_Amber | 1. <$20m | Not updated | 3_Amber
AGC | AGC_012 | Q2_2017 | Project Program 20 | 2010-04-01 | 2017-06-30 | Yes | 32785011 | 118060000 | 0 | 20-50% | None | $20m-$100m | <>25-50% | 59% | 29.71% | 2 | 1 | 4 | Assessor generated text | Most risks and mitigations are NOT logical, complete or current | All of the residual risks are low or medium | 3 | Assessor generated text | Program appears subject to re-prioritisation and scope changes by the agency. But risks and issues don’t reflect this. Suggest closer assurance to be done. | 3 - Population - High | 1 - Quantum - Low | 5 | Assessor generated text | Assessor generated text | Assessor generated text | 1826 | Engage | 4 | Program | Agency generated text | 1 | Amber | 2018.5 | 2018 | 27 | Green | $11.1M | Agency generated text | firstname.lastname@Agency-C.gov.au | firstname.lastname@AGC_012.gov.au | 3_Engage | 3_Amber | 1. <$20m | Not updated | 3_Amber

## PP_Benefits
ProjectID | CollectionRound | BenefitID | Benefit_DateOfLastUpdate | Benefit_Description | Benefit_RealisationStartDate | Benefit_Status | Benefit_Assessor_Note | Overall_Benefit_Viability_Assessor | Overall_Benefit_Status_Assessor | Overall_Benefit_Rating | StartDate | Benefit_Status_Rating | Age_Year
AGA_001 | Q2_2017 | AGA_001_B_01 | 2018-12-30 | Agency-Generated Text | 2017-07-01 | 2_On Track | blah blah | 4 | 3 | 1 | 2015-01-01 | 2 | 2017.5
AGA_002 | Q2_2017 | AGA_002_B_01 |  | Agency-Generated Text | 2015-01-01 | 2_On Track | [5 empty] | 2 | 2016
AGA_003 | Q2_2017 | AGA_003_B_01 |  | Agency-Generated Text | 2015-06-01 | 2_On Track | [5 empty] | 2
AGA_004 | Q2_2017 | AGA_004_B_01 |  | Agency-Generated Text | 2018-07-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGA_005 | Q2_2017 | AGA_005_B_01 |  | Agency-Generated Text | 2015-01-01 | 2_On Track | [5 empty] | 2 | 2015.9231
AGB_001 | Q2_2017 | AGB_001_B_01 |  | Agency-Generated Text | 2017-07-01 | 2_On Track | [5 empty] | 2 | 2015.4231
AGB_002 | Q2_2017 | AGB_002_B_01 |  | Agency-Generated Text | 2017-07-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGB_003 | Q2_2017 | AGB_003_B_01 |  | Agency-Generated Text | 2017-07-01 | 2_On Track | [5 empty] | 2 | 2018.4808
AGC_001 | Q2_2017 | AGC_001_B_01 |  | Agency-Generated Text | 2017-06-30 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_002 | Q2_2017 | AGC_002_B_01 |  | Agency-Generated Text | 2015-12-31 | 2_On Track | [5 empty] | 2 | 2018.9808
AGC_003 | Q2_2017 | AGC_003_B_01 |  | Agency-Generated Text | 2015-01-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_004 | Q2_2017 | AGC_004_B_01 |  | Agency-Generated Text | 2015-06-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_005 | Q2_2017 | AGC_005_B_01 |  | Agency-Generated Text | 2017-07-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_006 | Q2_2017 | AGC_006_B_01 |  | Agency-Generated Text | 2018-12-30 | 2_On Track | [5 empty] | 2 | 2016
AGC_007 | Q2_2017 | AGC_007_B_01 |  | Agency-Generated Text | 2017-07-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_008 | Q2_2017 | AGC_008_B_01 |  | Agency-Generated Text | 2018-12-30 | 2_On Track | [5 empty] | 2 | 2015.4231
AGC_009 | Q2_2017 | AGC_009_B_01 |  | Agency-Generated Text | 2015-01-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_010 | Q2_2017 | AGC_010_B_01 |  | Agency-Generated Text | 2015-12-01 | 2_On Track | [5 empty] | 2 | 2011.5
AGC_011 | Q2_2017 | AGC_011_B_01 |  | Agency-Generated Text | 2015-01-01 | 2_On Track | [5 empty] | 2 | 2017.5
AGC_012 | Q2_2017 | AGC_012_B_01 |  | Agency-Generated Text | 2017-06-30 | 2_On Track | [5 empty] | 2 | 2018.9808

## PP_BusinessCategory
ProjectID | Business Category
AGA_001 | Invest in National Capability and Assets
AGA_002 | Payments Management
AGA_003 | Service Delivery
AGA_004 | Collection of Revenue
AGA_005 | Service Delivery
AGB_001 | Internal Government Resource Management
AGB_002 | Protect and Secure the Nation
AGB_003 | Invest in National Capability and Assets
AGC_001 | Collection of Revenue
AGC_002 | Service Delivery
AGC_003 | Payments Management
AGC_004 | Internal Government Resource Management
AGC_005 | Protect and Secure the Nation
AGC_006 | Protect and Secure the Nation
AGC_007 | Protect and Secure the Nation
AGC_008 | Protect and Secure the Nation
AGC_009 | Protect and Secure the Nation
AGC_010 | Protect and Secure the Nation
AGC_011 | Service Delivery
AGC_012 | Protect and Secure the Nation

## PP_Risks
ProjectID | CollectionRound | RiskID | Risk_DateOfLastUpdate | Risk_Description | Risk_Rating_Before_Mitigation | Risk_Mitigation_Strategy | Risk_Rating_After_Mitigation | Risk_Assessor_Note | Overall_Risk_LogicalCompleteCurrent | Overall_Risk_ResidualRisks | Overall_Risk_Assessor | Overall_Risk_ResidualRisks_Score | Overall_Risk_LogicalCompleteCurrent (groups)
AGA_001 | Q2_2017 | ABS_001_R_04 | 2017-03-12 | Negative public campaigns reducing public cooperation. | High | Agency-generated Text | 3_High | note from risk assessor | illogical, incomplete and out of date | residual |  | 3 | (Blank)
AGA_002 | Q2_2017 | ABS_001_R_05 |  | Phishing or man-in-the-middle attacks on responding public | High | Agency-generated Text | 3_High | [5 empty] | (Blank)
AGA_003 | Q2_2017 | ABS_001_R_06 |  | Systems/hardware failure | High | Agency-generated Text | 3_High | [5 empty] | (Blank)
AGA_004 | Q2_2017 | ABS_001_R_07 |  | Increased reliance on technology, including mobile technologies, and associated security issues | High | Agency-generated Text | 3_High | [5 empty] | (Blank)
AGA_005 | Q2_2017 | ABS_001_R_09 |  | Reliance on Mail as the main mechanism for seeking participation in the Census - potential for significant price increase or change in service | High | Agency-generated Text | 3_High | [5 empty] | (Blank)
AGB_001 | Q2_2017 | ABS_001_R_10 |  | Other Government activities e.g. other Government organisations provide support solutions that differ considerably to ABS', leading to the publiuc expectation not being met by ABS. | High | Agency-generated Text | 3_High | [5 empty] | (Blank)
AGB_002 | Q2_2017 | ABS_002_R_08 |  | There is a risk that the expectations of key external ABS stakeholders (e.g., the Minister, ANAO, Finance, the public, and media) are not adequately managed with respect to SBTP deliverables and expectations, such that stakeholders are sufficiently engaged and satisfied with the program and ABS. Impact: Support for and/or cooperation with ABS is reduced. Consequences: • reduce ability to produce reliable statistics • reputational damage. | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGB_003 | Q2_2017 | ABS_002_R_09 |  | There is the risk the new technologies delivered by the program may have vulnerabilities which may make it more susceptible to a cyber security attack. Impact: The potential loss of data or compromised systems. Consequence: significant reputational damage to both the program and ABS. | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_001 | Q2_2017 | AFP_001_R_01 |  | Interdependency between other programs not understood. | High | Agency-generated Text | 1_Low | [5 empty] | (Blank)
AGC_002 | Q2_2017 | AFP_001_R_02 |  | Lack of alignment between the Citadel and IIE Program Roadmaps | High | Agency-generated Text | 1_Low | [5 empty] | (Blank)
AGC_003 | Q2_2017 | AFP_001_R_03 |  | Solution not acceptable or unlawful or user access either too restricted or too open | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_004 | Q2_2017 | AFP_001_R_04 |  | Lack of understanding of Executive roles, responsibilities, accountabilities and insufficient business buy-in | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_005 | Q2_2017 | AFP_001_R_05 |  | Delays to work committed by the program | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_006 | Q2_2017 | AFP_001_R_06 |  | Interdependency between IIE and ISCS/Rampart Programs not agreed | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_007 | Q2_2017 | AFP_002_R_01 |  | Resourcing Contraints | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_008 | Q2_2017 | AFP_002_R_02 |  | Acceptance of the change | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_009 | Q2_2017 | AFP_002_R_03 |  | EOL Equipment fails before replacement | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_010 | Q2_2017 | AFP_002_R_04 |  | Impacts of other projects on program deliverables | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_011 | Q2_2017 | AFP_004_R_01 |  | Impacts of other projects on program deliverables | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)
AGC_012 | Q2_2017 | AFP_004_R_02 |  | Lack of Data Centre Governance | High | Agency-generated Text | 2_Medium | [5 empty] | (Blank)

## CBS
Portfolio | AgencyShortName | CBS ID | Name | Duplication | Responsible Agency | Risk | Business Category | Risk (groups)
Portfolio_I | AGA_001 | AGA_001_001 | Agency provided unique CBS name - 1 | No |  | Low | Protect and Secure the Nation | 1_Low
Portfolio_I | AGA_002 | AGA_002_001 | Agency provided unique CBS name - 2 | No |  | Medium | Regulate Non-Government Activity | 3_High
Portfolio_I | AGA_003 | AGA_003_001 | Agency provided unique CBS name - 3 | No |  | Low | Invest in National Capability and Assets | 2_Medium
Portfolio_I | AGA_004 | AGA_004_001 | Agency provided unique CBS name - 4 | No |  | Low | Internal Government Resource Management | 1_Low
Portfolio_I | AGA_005 | AGA_005_001 | Agency provided unique CBS name - 5 | No |  | Medium | Regulate Non-Government Activity | 2_Medium
Portfolio_I | AGB_001 | AGB_001_001 | Agency provided unique CBS name - 6 | No |  | Medium | Manage National Agenda | 1_Low
Portfolio_I | AGB_002 | AGB_002_001 | Agency provided unique CBS name - 7 | No |  | Medium | Internal Government Resource Management | 3_High
Portfolio_I | AGB_003 | AGB_003_001 | Agency provided unique CBS name - 8 | No |  | Medium | Service Delivery | 3_High
Portfolio_II | AGC_001 | AGC_001_001 | Agency provided unique CBS name - 9 | No |  | Medium | Service Delivery | 1_Low
Portfolio_II | AGC_002 | AGC_002_001 | Agency provided unique CBS name - 10 | No |  | Low | Protect and Secure the Nation | 1_Low
Portfolio_II | AGC_003 | AGC_003_001 | Agency provided unique CBS name - 11 | No |  | Medium | Service Delivery | 1_Low
Portfolio_II | AGC_004 | AGC_004_001 | Agency provided unique CBS name - 12 | No |  | High | Payments Management | 2_Medium
Portfolio_II | AGC_005 | AGC_005_001 | Agency provided unique CBS name - 13 | No |  | Medium | Manage National Agenda | 3_High
Portfolio_II | AGC_006 | AGC_006_001 | Agency provided unique CBS name - 14 | No |  | Medium | Payments Management | 2_Medium
Portfolio_II | AGC_007 | AGC_007_001 | Agency provided unique CBS name - 15 | No |  | Low | Protect and Secure the Nation | 1_Low
Portfolio_II | AGC_008 | AGC_008_001 | Agency provided unique CBS name - 16 | No |  | Low | Service Delivery | 2_Medium
Portfolio_II | AGC_009 | AGC_009_001 | Agency provided unique CBS name - 17 | No |  | Low | Service Delivery | 1_Low
Portfolio_II | AGC_010 | AGC_010_001 | Agency provided unique CBS name - 18 | No |  | Low | Grants and Loans Management | 2_Medium
Portfolio_II | AGC_011 | AGC_011_001 | Agency provided unique CBS name - 19 | No |  | Medium | Service Delivery | 1_Low
Portfolio_II | AGC_012 | AGC_012_001 | Agency provided unique CBS name - 20 | No |  | Low | Service Delivery | 3_High

## PP_Avg_Risk_Level
ProjectID | Average of Risk Level | Overall_Risk_LogicalCompleteCurrent (groups)
AGA_001 | 2 | 3
AGA_002 | 1.5 | 3
AGA_003 | 1.89 | 1
AGA_004 | 2.41 | 3
AGA_005 | 1.25 | 3
AGB_001 | 1.89 | 3
AGB_002 | 1.81 | 2
AGB_003 | 2 | 2
AGC_001 | 2 | 2
AGC_002 | 1.5 | 2
AGC_003 | 1.94 | 2
AGC_004 | 1.8 | 1
AGC_005 | 1.75 | 2
AGC_006 | 1.11 | 2
AGC_007 | 2 | 1
AGC_008 | 1.11 | 3
AGC_009 | 2.5 | 2
AGC_010 | 2.41 | 3
AGC_011 | 1.65 | 2
AGC_012 | 1.11 | 2